## QA Issues
CRM - Light/Dark Mode QA Findings
Scope: pages worked on this session - Sidebar (nav/drawer/collapsed), Dashboard, Settings (all panels, Modules & Fields incl. Layout Editor + New Layout Builder), Reports
# | Page / Component | Mode(s) Affected | Issue | Severity | Status | Root Cause | Recommended Fix | Notes
1 | Settings > Modules and Fields > Leads > Layouts table | Dark mode only | Clickable layout name ("Base Layout") loses its blue link color and renders as plain gray text, removing the visual affordance that it is clickable. | Medium | Open | Global CSS safety-net in app/globals.css (html.dark .text-[#1D4ED8] { color: #D4D4D8 !important; }) blanket-converts all blue #1D4ED8 text to gray in dark mode, including intentional link text. | Give interactive links a distinct dark-mode link color (e.g. #60A5FA) via an explicit class instead of relying on the blanket #1D4ED8-to-gray override, or exclude link elements from the global override. | Same override likely affects other blue links elsewhere in the app that were not explicitly re-themed with #60A5FA (e.g. other list views using #1D4ED8 for row links).
2 | Settings > Modules and Fields > [Module] > Fields tab (Field Listing toolbar) | Both light & dark | Search input ("Search Fields or Data Types") is squeezed to ~82px next to the "All Layouts" dropdown and "Create and Edit Fields" button, truncating the placeholder text to "Searc" at laptop-width viewports. | Medium | Open | Toolbar row lacks a min-width / responsive stacking rule for the search input; the 3-pane Modules & Fields layout (settings sidebar + module list + detail panel) leaves too little horizontal room at ~900-1280px widths. | Add min-w-[160px] (or similar) to the search input, and/or let the toolbar wrap to a second line below ~1024px instead of compressing the search field. | Not a theme/color bug - reproduces identically in both light and dark mode. Worth a follow-up responsive-layout pass.
3 | Sidebar - profile card ("PM SDL" / "Admin . email") - mobile drawer & desktop expanded | Both light & dark | Subtitle text ("Admin . dmops@socialdnalabs.com") is very low contrast at only 10px font size - text-slate-400 (~2.4:1) in light mode, text-[#71717A] (~3.5:1) in dark mode. | Low | Open | Font size (10px) combined with a mid-gray color falls below WCAG AA's 4.5:1 contrast requirement for normal text in both themes; pre-existing styling, not introduced by this session's fixes. | Bump subtitle color to a darker/lighter shade with sufficient contrast (e.g. slate-500/#9CA3AF) and/or increase font size to 11-12px. | Pre-existing issue, unrelated to the dark-mode fixes applied this session.

## Verified Clean
Verified Clean - No Issues Found
Page / Component | Light Mode | Dark Mode | Notes
Dashboard (KPI cards, Revenue Trend, Pipeline by Stage, Recent Deals, Recent Activity) | OK | OK | Glass-morphism cards adapt correctly; header renders correctly dark/light (initial computed-style read was a sandbox artifact, confirmed via screenshot).
Settings > Personal Settings | OK | OK | Profile hero, User/Role/More Information cards all theme correctly.
Settings > Users (list + detail panel) | OK | OK | Active nav item highlight confirmed correct via class inspection despite a misleading hover-cursor artifact in one screenshot.
Settings > Organization | OK | OK | General/Contact Information cards theme correctly.
Settings > Roles (Tree/List view, Role Information panel) | OK | OK | Tree/List toggle pill and role detail panel have correct contrast.
Settings > Permissions (matrix) | OK | OK | Permission toggle matrix renders cleanly in dark mode.
Settings > Email / Import / Export / Data Backup (placeholders) | OK | OK | Placeholder panels correctly themed.
Settings > Customize Home Page | OK | OK | Create Home Page button correctly dark-themed (#18181B bg / white text) - initial visual read was misleading, confirmed via computed styles.
Settings > Modules and Fields (module list, Layouts tab) | OK | OK | Table, badges, and Create New Layout button theme correctly.
Settings > Modules and Fields > Layout Editor (existing Base Layout) | OK | OK | Fixed this session: Layout Name input, canvas, New Fields chips, Create/Quick Create/Detail View tabs, Business Card Customize modal all confirmed dark-themed via screenshot.
Settings > Modules and Fields > New Layout Builder (Create New Layout flow) | OK | OK | Fixed this session: same coverage as Layout Editor, plus Preview modal.
Reports (list page) | OK | OK | Report name links correctly use #60A5FA in dark mode (built with isDark-aware styling from the start, unaffected by the global override issue found elsewhere).
Sidebar - main nav links, Settings link hover states | OK | OK | Hover contrast issues fixed earlier this session (desktop expanded/collapsed + mobile drawer).