## QA Issues
CRM - Master QA Findings (All Modules)
Scope: UI/UX only (Create/Update/Delete persistence is owned by the backend team and out of scope). Covers Dashboard, Leads, Deals, Contacts, Accounts, Tasks, Reports, Settings.
# | Category | Page / Component | Mode(s) Affected | Issue | Severity | Status | Root Cause | Recommended Fix | Notes
1 | Data Consistency | Contacts > Contact Detail page (all contacts) | Both light & dark | The record ID field labeled "ID:" displays the contact's own name (e.g. "ID: Cop Mar") instead of a proper record reference like Leads' "CRM-LEAD-0001" or Deals' "CRM DEAL 2026 00001". | High | Open | components/contacts/ContactDetail.tsx: every contact record's refId field was populated with the contact's name string instead of a generated ID (e.g. line 61: refId: "Cop Mar" for a contact named Cop Mar). | Generate a proper CRM-CONTACT-XXXX style refId for each contact record, matching the Leads/Deals ID convention. | Confirmed by inspecting all sample records in ContactDetail.tsx - refId always equals the contact's own name, not a one-off typo.
2 | Cross-Module Consistency | Detail pages - record ID display (Leads / Deals / Contacts / Accounts / Tasks) | Both light & dark | Each module formats its record ID differently: Leads shows "Lead ID: CRM-LEAD-0001", Deals shows "CRM DEAL 2026 00001", Accounts shows a raw "ID #1", Tasks shows a raw "Task . #19", and Contacts shows the bug in finding #1. No shared ID convention exists across modules. | Medium | Open | Each detail component was built independently with its own refId/id display logic and no shared ID-formatting utility or convention. | Define one ID format convention (e.g. CRM-{MODULE}-{number}) and apply it consistently across all 5 detail components. | Cross-checked directly against source in LeadDetail.tsx, DealDetail.tsx, AccountDetail.tsx, TaskDetail.tsx, ContactDetail.tsx.
3 | Functional / Data Layer (informational, not being fixed) | App-wide - all "New X" drawers (Leads, Deals, Contacts, Accounts, Tasks) + Edit + Delete | N/A - functional, not visual | Create, Update, and Delete are all no-ops: submitting a completely empty required form succeeds silently with no validation, edits don't persist to the record, and Delete menu items have no handler wired. | High | Blocked (backend) | Every drawer's handleSubmit is a stub: console.log(form); onClose(). No persistence layer exists yet - confirmed as owned by the separate backend team, so out of scope for this QA pass. | N/A for this pass - backend team is implementing real persistence separately. Re-test once wired. | Logged for visibility only. Confirmed via direct testing: empty-field submit, an edited-then-saved name that reverted, and an unwired Delete Lead menu item.
4 | Duplicate UI / Layout Bug | Leads > Lead Detail page | Both light & dark | Lead detail pages rendered TWO stacked <header> bars (global AppHeader + a page-local TopBar with duplicate theme-toggle/bell/avatar). | High | Fixed | components/leads/LeadDetail.tsx:214 had an active <TopBar /> call while the 4 sibling detail components had it commented out. | Commented out the stray <TopBar /> call to match DealDetail/ContactDetail/AccountDetail/TaskDetail. | Verified fixed: only one <header> (64px) now renders on Lead detail.
5 | Broken Navigation | Main Sidebar - Customer Comms link | Both light & dark | The "Customer Comms" nav item linked to /comms, which rendered Next.js's default 404 page. | High | Fixed | Route /comms did not exist in the app directory. | Built app/comms/page.tsx as a themed "coming soon" placeholder consistent with the app's other placeholder panels. | Verified fixed: /comms now renders a proper themed placeholder instead of a 404.
6 | Cross-Page Consistency | Tasks list page toolbar | Both light & dark | Tasks was the only list page missing "Columns" and "Sort" controls that Leads/Deals/Contacts/Accounts all have; its grid columns also had sorting completely disabled (sortable: false on every column). | Medium | Fixed | TasksPage toolbar was built with a reduced button set; grid columns never had a sort mechanism wired. | Added Columns (checkbox visibility menu) and Sort (reused SortPopover, generalized with an optional columns prop) to match other modules; verified no regression on Leads' existing Sort. | Verified fixed via live interaction: Sort popover opens with Task-specific columns, Columns menu correctly hides/shows grid columns.
7 | Dark Mode Theming | Settings > Modules and Fields > Leads > Layouts table | Dark mode only | Clickable layout name ("Base Layout") lost its blue link color and rendered as plain gray text. | Medium | Fixed | Global CSS safety-net (html.dark .text-[#1D4ED8] { color: #D4D4D8 !important; }) blanket-converted the link's blue text to gray. | Replaced the Tailwind class with an inline style (#60A5FA in dark) that bypasses the class-based override. | Verified fixed: computed color now rgb(96,165,250) = #60A5FA.
8 | Responsive Layout | Settings > Modules and Fields > [Module] > Fields tab (Field Listing toolbar) | Both light & dark | Search input was squeezed to ~82px next to the dropdown and button, truncating its placeholder to "Searc" at laptop-width viewports. | Medium | Fixed | Toolbar row lacked a min-width / wrap rule for the search input. | Added min-w-[160px] and flex-wrap to the toolbar so it wraps instead of compressing. | Verified fixed: full placeholder "Search Fields or Data Types" now visible, toolbar wraps at this viewport.
9 | Accessibility / Contrast | Sidebar - profile card (mobile drawer & desktop expanded) | Both light & dark | Subtitle text ("Admin . email") was low contrast at only 10px - ~2.4:1 in light mode, ~3.5:1 in dark mode, both below WCAG AA's 4.5:1. | Low | Fixed | Font size (10px) combined with a mid-gray color fell below the AA contrast requirement in both themes. | Bumped to 11px and darker/lighter shade (slate-500 / #9CA3AF). | Verified fixed via class inspection; new contrast ratios pass AA for both themes.
10 | Layout / Overflow Bug | Settings > Personal Settings & Users > detail panel (User Information card) | Both light & dark | Email value overflowed its grid cell and visually overlapped the adjacent Mobile No value (e.g. rendered as "pm@socialdnalabs.co7788778855"). | High | Fixed | app/settings/page.tsx - the shared KV component's value <div> (~line 204) had no truncate/overflow-hidden class, so long values like emails overflowed their 2-column grid cell (KVGrid, ~96px wide) into the neighboring field. | Added truncate class plus a title tooltip (full value on hover) to the KV value div. | Verified fixed in both themes: email now truncates cleanly (e.g. "pm@sociald...") with Mobile No fully visible, no overlap.
11 | Component / Label Bug | Settings > Users > "New User" dialog > More Information > Gender field | Both light & dark | Gender dropdown was missing its visible field label; the "Gender" InputLabel rendered overlapping the "Select gender" placeholder text instead of shrinking to the notched position above the field like the other fields (Role, Date of Birth, etc.). | Medium | Fixed | app/settings/page.tsx (~line 509): MUI does not auto-shrink an InputLabel for an outlined Select using displayEmpty with an empty string value, so the label stayed inline and overlapped the placeholder. | Added the shrink prop to the InputLabel so it renders in the notched position consistent with sibling fields. | Verified fixed in both themes: "Gender" label now shows above the field, placeholder renders cleanly with no overlap.
12 | Dead Control | Reports (list page) and Report Detail page - Filter button | Both light & dark | Filter icon button in the toolbar produces no visible effect when clicked - no popover, panel, or other feedback opens. | Medium | Open | Not yet investigated - likely an unwired onClick handler or a filter panel that was never built. | Wire the Filter button to a real filter panel/popover, or hide it until the feature is implemented. | Confirmed via direct click testing on both the Reports list toolbar and the Report Detail toolbar; no DOM/visual change in either case.
13 | Dead Control | Reports list page - row kebab (⋮) menu | Both light & dark | Clicking the three-dot row menu only shows a hover highlight; no dropdown menu of row actions ever opens. | Medium | Open | Not yet investigated - likely an unwired onClick handler or menu component that was never attached. | Wire the kebab button to open a real actions menu (e.g. Open, Rename, Delete, Duplicate). | Confirmed via direct click testing on multiple report rows; button shows :hover state only.
14 | Dead / Unclear Control | Report Detail page - Grid view / List view toggle | Both light & dark | Clicking the Grid view / List view icons in the toolbar produces no visible layout change to the report content. | Low | Open | Not yet investigated - toggle may be unwired, or the two views may be visually identical for this report type. | Verify intended behavior with product; either implement a visible layout difference or remove the toggle if not applicable to reports. | Confirmed via direct click testing; no visible change in chart/table layout after toggling.
15 | Incomplete Feature | Settings > Permissions page - "Summary View" tab | Both light & dark | "Summary View" tab becomes visually selected/active when clicked, but renders identical content to the "Permission Matrix" tab - appears to be an unimplemented alternate view. | Low | Open | Summary View tab likely has no distinct render branch yet; both tabs point at the same Permission Matrix content. | Implement a distinct summary rendering, or remove the tab until the feature is built. | Confirmed by switching tabs and diffing rendered content; both tab states show the same permission grid.

## Consistency Matrix
Cross-Module Consistency Check
Page | Record ID Format | H1 Font Size / Weight | Toolbar Controls | View Toggles | Notes
Leads | Lead ID: CRM-LEAD-0001 (formatted) | 22px / 600 | Search, Filters, Columns, Sort | List, Grid, Kanban | Baseline reference.
Deals | CRM DEAL 2026 00001 (formatted, different style) | 22px / 600 | Search, Filters, Columns, Sort | List, Grid, Kanban | Different ID punctuation than Leads (no hyphens) - see Consistency issue #2.
Contacts | Bug: shows contact's own name, not an ID | 22px / 600 (visual match) | Search, Filters, Columns, Sort | List, Grid | See QA Issues #1 - High severity data bug.
Accounts | ID #1 (raw internal id, unformatted) | 22px / 600 (visual match) | Search, Filters, Columns, Sort | List, Grid | No CRM-ACCOUNT-XXXX style formatting.
Tasks | Task . #19 (raw internal id, unformatted) | 22px / 600 (visual match) | Search, Filters, Columns, Sort (fixed this session) | List, Grid | Columns/Sort added this session to match other modules.
Reports | N/A - different page type | 22px extrabold (heavier than list pages) | Search only (by design - different record type) | N/A (table only) | Reduced toolbar is expected for a reports list, not a bug.

## Verified Clean
Verified Clean - No Issues Found
Page / Component | Light Mode | Dark Mode | Notes
Dashboard (KPI cards, Revenue Trend, Pipeline by Stage, Recent Deals, Recent Activity) | OK | OK | Glass-morphism cards adapt correctly in both themes.
Settings > Personal Settings / Users / Organization / Roles / Permissions | OK | OK | All panels theme correctly, including toggle matrix and role tree.
Settings > Email / Import / Export / Data Backup (placeholders) | OK | OK | Placeholder panels correctly themed.
Settings > Customize Home Page | OK | OK | Create Home Page button correctly dark-themed.
Settings > Modules and Fields (module list, Layout Editor, New Layout Builder) | OK | OK | Layout Name input, canvas, field chips, all 3 tabs, Business Card modal, Preview modal all confirmed dark-themed.
Reports (list page) | OK | OK | Report name links correctly use #60A5FA in dark mode - built isDark-aware from the start.
Sidebar - main nav links + hover states + profile card | OK | OK | Hover contrast and low-contrast subtitle both fixed this session.
Leads - List / Grid / Kanban views | OK | OK | Table, cards, kanban columns, avatars all theme correctly.
Leads - New Lead / Edit Lead drawer (UI only) | OK | OK | Form sections, inputs, dropdowns, required-field asterisks all render correctly. (Underlying save does not persist - see QA Issues #3.)
Leads - empty search state | OK | OK | "No leads found" empty state renders cleanly with icon, heading, and helper text in both themes.
Deals - List view + Detail page | OK | OK | Pipeline value badge, stage chips, probability bars, KPI tiles all theme correctly. Single clean header (no duplicate-header bug, unlike pre-fix Leads).
Contacts - List view + Detail page (aside from ID bug) | OK | OK | Table and detail cards render correctly; only the ID field itself is wrong (see QA Issues #1).
Accounts - List view + Detail page (aside from ID format) | OK | OK | Colored account-initial avatars, table, and detail cards render correctly.
Tasks - List view + Detail page (aside from ID format) | OK | OK | Priority/status chips and table theme correctly.